{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["管理表","Table"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"管理表","index":0,"n_rows":286,"n_cols":189,"rows_kept":286,"cut":false,"hidden":false,"merged":[[11,1,12,4],[11,5,12,5],[11,6,12,6],[11,7,12,7],[11,8,12,8],[11,9,12,9],[4,3,4,4],[5,3,5,4],[4,7,4,9],[5,7,5,9],[6,7,6,9],[4,1,4,2],[5,1,5,2],[6,1,6,2],[127,3,132,3],[115,3,120,3],[103,3,108,3],[97,3,102,3],[85,3,90,3],[205,3,210,3],[193,3,198,3],[187,3,192,3],[223,3,228,3],[211,3,216,3],[217,3,222,3],[109,3,114,3],[121,3,126,3],[266,19,266,63],[267,19,267,63],[264,5,265,5],[264,8,265,8],[264,19,265,63],[133,3,138,3],[256,9,258,9],[247,3,252,3],[247,4,252,4],[247,5,252,5],[247,6,249,6],[247,7,249,7],[247,8,249,8],[247,9,249,9],[250,6,252,6],[253,3,258,3],[253,4,258,4],[253,5,258,5],[253,6,255,6],[253,7,255,7],[256,6,258,6],[256,7,258,7],[241,3,246,3],[241,4,246,4],[285,222,285,282],[253,8,255,8],[253,9,255,9],[256,8,258,8],[272,222,272,282],[273,222,273,282],[272,10,272,18],[273,10,273,18],[270,222,270,282],[271,222,271,282],[271,10,271,18],[270,19,270,63],[268,222,268,282],[269,222,269,282],[268,19,268,63],[269,19,269,63],[271,19,271,63],[272,19,272,63],[273,19,273,63],[274,19,274,63],[275,19,275,63],[276,19,276,63],[266,222,266,282],[267,222,267,282],[241,5,246,5],[241,6,243,6],[250,7,252,7],[250,8,252,8],[250,9,252,9],[235,3,240,3],[235,4,240,4],[235,5,240,5],[235,6,237,6],[235,7,237,7],[235,8,237,8],[241,7,243,7],[241,8,243,8],[241,9,243,9],[244,6,246,6],[244,7,246,7],[244,8,246,8],[244,9,246,9],[235,9,237,9],[238,6,240,6],[238,7,240,7],[238,8,240,8],[238,9,240,9],[211,4,216,4],[211,5,216,5],[211,6,213,6],[211,7,213,7],[211,8,213,8],[211,9,213,9],[214,6,216,6],[214,7,216,7],[214,8,216,8],[214,9,216,9],[217,8,219,8],[217,9,219,9],[220,6,222,6],[220,7,222,7],[220,8,222,8],[220,9,222,9],[217,4,222,4],[217,5,222,5],[217,6,219,6],[217,7,219,7],[229,8,231,8],[229,9,231,9],[232,6,234,6],[232,7,234,7],[232,8,234,8],[232,9,234,9],[229,3,234,3],[229,4,234,4],[229,5,234,5],[229,6,231,6],[229,7,231,7],[223,4,228,4],[223,5,228,5],[223,6,225,6],[223,7,225,7],[223,8,225,8],[223,9,225,9],[226,6,228,6],[226,7,228,7],[226,8,228,8],[226,9,228,9],[19,8,21,8],[19,9,21,9],[22,6,24,6],[22,7,24,7],[22,8,24,8],[22,9,24,9],[19,3,24,3],[19,4,24,4],[19,5,24,5],[19,6,21,6],[19,7,21,7],[175,8,177,8],[175,9,177,9],[178,6,180,6],[178,7,180,7],[178,8,180,8],[178,9,180,9],[175,3,180,3],[175,4,180,4],[175,5,180,5],[175,6,177,6],[175,7,177,7],[169,8,171,8],[169,9,171,9],[172,6,174,6],[172,7,174,7],[172,8,174,8],[172,9,174,9],[169,3,174,3],[169,4,174,4],[169,5,174,5],[169,6,171,6],[169,7,171,7],[181,8,183,8],[181,9,183,9],[184,6,186,6],[184,7,186,7],[184,8,186,8],[184,9,186,9],[181,3,186,3],[181,4,186,4],[181,5,186,5],[181,6,183,6],[181,7,183,7],[187,4,192,4],[187,5,192,5],[187,6,189,6],[187,7,189,7],[187,8,189,8],[187,9,189,9],[190,6,192,6],[190,7,192,7],[190,8,192,8],[190,9,192,9],[193,4,198,4],[193,5,198,5],[193,6,195,6],[193,7,195,7],[193,8,195,8],[193,9,195,9],[196,6,198,6],[196,7,198,7],[196,8,198,8],[196,9,198,9],[199,8,201,8],[199,9,201,9],[202,6,204,6],[202,7,204,7],[202,8,204,8],[202,9,204,9],[199,3,204,3],[199,4,204,4],[199,5,204,5],[199,6,201,6],[199,7,201,7],[205,4,210,4],[205,5,210,5],[205,6,207,6],[205,7,207,7],[205,8,207,8],[205,9,207,9],[208,6,210,6],[208,7,210,7],[208,8,210,8],[208,9,210,9],[145,8,147,8],[145,9,147,9],[148,6,150,6],[148,7,150,7],[148,8,150,8],[148,9,150,9],[145,3,150,3],[145,4,150,4],[145,5,150,5],[145,6,147,6],[145,7,147,7],[151,8,153,8],[151,9,153,9],[154,6,156,6],[154,7,156,7],[154,8,156,8],[154,9,156,9],[151,3,156,3],[151,4,156,4],[151,5,156,5],[151,6,153,6],[151,7,153,7],[157,8,159,8],[157,9,159,9],[160,6,162,6],[160,7,162,7],[160,8,162,8],[160,9,162,9],[157,3,162,3],[157,4,162,4],[157,5,162,5],[157,6,159,6],[157,7,159,7],[163,8,165,8],[163,9,165,9],[166,6,168,6],[166,7,168,7],[166,8,168,8],[166,9,168,9],[163,3,168,3],[163,4,168,4],[163,5,168,5],[163,6,165,6],[163,7,165,7],[31,8,33,8],[31,9,33,9],[34,6,36,6],[34,7,36,7],[34,8,36,8],[34,9,36,9],[31,3,36,3],[31,4,36,4],[31,5,36,5],[31,6,33,6],[31,7,33,7],[37,8,39,8],[37,9,39,9],[40,6,42,6],[40,7,42,7],[40,8,42,8],[40,9,42,9],[37,3,42,3],[37,4,42,4],[37,5,42,5],[37,6,39,6],[37,7,39,7],[43,8,45,8],[43,9,45,9],[46,6,48,6],[46,7,48,7],[46,8,48,8],[46,9,48,9],[43,3,48,3],[43,4,48,4],[43,5,48,5],[43,6,45,6],[43,7,45,7],[49,8,51,8],[49,9,51,9],[52,6,54,6],[52,7,54,7],[52,8,54,8],[52,9,54,9],[49,3,54,3],[49,4,54,4],[49,5,54,5],[49,6,51,6],[49,7,51,7],[55,8,57,8],[55,9,57,9],[58,6,60,6],[58,7,60,7],[58,8,60,8],[58,9,60,9],[55,3,60,3],[55,4,60,4],[55,5,60,5],[55,6,57,6],[55,7,57,7],[61,8,63,8],[61,9,63,9],[64,6,66,6],[64,7,66,7],[64,8,66,8],[64,9,66,9],[61,3,66,3],[61,4,66,4],[61,5,66,5],[61,6,63,6],[61,7,63,7],[67,8,69,8],[67,9,69,9],[70,6,72,6],[70,7,72,7],[70,8,72,8],[70,9,72,9],[67,3,72,3],[67,4,72,4],[67,5,72,5],[67,6,69,6],[67,7,69,7],[73,8,75,8],[73,9,75,9],[76,6,78,6],[76,7,78,7],[76,8,78,8],[76,9,78,9],[73,3,78,3],[73,4,78,4],[73,5,78,5],[73,6,75,6],[73,7,75,7],[79,8,81,8],[79,9,81,9],[82,6,84,6],[82,7,84,7],[82,8,84,8],[82,9,84,9],[79,3,84,3],[79,4,84,4],[79,5,84,5],[79,6,81,6],[79,7,81,7],[85,4,90,4],[85,5,90,5],[85,6,87,6],[85,7,87,7],[85,8,87,8],[85,9,87,9],[88,6,90,6],[88,7,90,7],[88,8,90,8],[88,9,90,9],[91,8,93,8],[91,9,93,9],[94,6,96,6],[94,7,96,7],[94,8,96,8],[94,9,96,9],[91,3,96,3],[91,4,96,4],[91,5,96,5],[91,6,93,6],[91,7,93,7],[97,4,102,4],[97,5,102,5],[97,6,99,6],[97,7,99,7],[97,8,99,8],[97,9,99,9],[100,6,102,6],[100,7,102,7],[100,8,102,8],[100,9,102,9],[112,7,114,7],[112,8,114,8],[112,9,114,9],[109,4,114,4],[109,5,114,5],[109,6,111,6],[109,7,111,7],[103,4,108,4],[103,5,108,5],[103,6,105,6],[103,7,105,7],[103,8,105,8],[103,9,105,9],[106,6,108,6],[106,7,108,7],[106,8,108,8],[106,9,108,9],[121,4,126,4],[121,5,126,5],[121,6,123,6],[121,7,123,7],[115,4,120,4],[115,5,120,5],[115,6,117,6],[115,7,117,7],[127,8,129,8],[118,6,120,6],[118,7,120,7],[118,8,120,8],[115,8,117,8],[139,5,144,5],[139,6,141,6],[139,7,141,7],[127,9,129,9],[130,6,132,6],[130,7,132,7],[130,8,132,8],[130,9,132,9],[121,8,123,8],[121,9,123,9],[124,6,126,6],[124,7,126,7],[124,8,126,8],[124,9,126,9],[25,3,30,3],[25,4,30,4],[25,5,30,5],[25,6,27,6],[25,7,27,7],[25,1,30,2],[139,8,141,8],[139,9,141,9],[133,4,138,4],[133,5,138,5],[133,6,135,6],[133,7,135,7],[133,8,135,8],[133,9,135,9],[136,6,138,6],[136,7,138,7],[136,8,138,8],[136,9,138,9],[127,4,132,4],[127,5,132,5],[127,6,129,6],[127,7,129,7],[139,3,144,3],[139,4,144,4],[235,1,240,2],[241,1,246,2],[211,1,216,2],[217,1,222,2],[223,1,228,2],[79,1,84,2],[73,1,78,2],[181,1,186,2],[175,1,180,2],[169,1,174,2],[229,1,234,2],[285,2,285,4],[264,9,265,9],[264,10,265,18],[266,10,266,18],[267,10,267,18],[268,10,268,18],[269,10,269,18],[270,10,270,18],[266,2,266,4],[267,2,267,4],[268,2,268,4],[269,2,269,4],[270,2,270,4],[271,2,271,4],[285,10,285,18],[264,1,265,1],[15,1,16,3],[264,2,265,4],[187,1,192,2],[193,1,198,2],[199,1,204,2],[205,1,210,2],[109,1,114,2],[115,1,120,2],[121,1,126,2],[127,1,132,2],[133,1,138,2],[139,1,144,2],[55,1,60,2],[49,1,54,2],[43,1,48,2],[37,1,42,2],[31,1,36,2],[163,1,168,2],[157,1,162,2],[151,1,156,2],[145,1,150,2],[253,1,258,2],[247,1,252,2],[25,8,27,8],[25,9,27,9],[28,6,30,6],[28,7,30,7],[283,19,283,63],[284,19,284,63],[285,19,285,63],[277,19,277,63],[278,19,278,63],[279,19,279,63],[280,19,280,63],[281,19,281,63],[282,19,282,63],[28,8,30,8],[28,9,30,9],[142,6,144,6],[142,7,144,7],[142,8,144,8],[142,9,144,9],[115,9,117,9],[118,9,120,9],[109,8,111,8],[109,9,111,9],[112,6,114,6],[1,7,1,8],[283,2,283,4],[284,2,284,4],[274,2,274,4],[275,2,275,4],[276,2,276,4],[277,2,277,4],[278,2,278,4],[279,2,279,4],[280,2,280,4],[281,2,281,4],[282,2,282,4],[14,1,14,4],[17,1,17,4],[18,1,18,4],[272,2,272,4],[273,2,273,4],[85,1,90,2],[91,1,96,2],[97,1,102,2],[103,1,108,2],[19,1,24,2],[67,1,72,2],[61,1,66,2]]}
[]
[null,"計画系業務スケジュール管理表",null,null,null,null,"更新日","2020-11-13"]
[]
[null,"【1.概要】"]
[null,"業務名",null,"○○管内交通量検討業務",null,"管理技術者",null,"○○○○"]
[null,"受注者名",null,"△△社",null,"担当技術者（主）",null,"△△△△"]
[null,"契約額",null,10000000,"円　（消費税込み）","担当技術者（副）",null,"□□□□"]
[null,"工期（自）",null,"2020-04-01"]
[null,"工期（至）",null,"2020-12-15"]
[]
[null,"【2.スケジュール】",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,null,null,null,1,null,null,null,null,null,null,null,null,null,1]
[null,"作業項目",null,null,null,"実施\n状況","区分","着手日\n上段：計画\n下段：実績","完了日\n上段：計画\n下段：実績","期間（日）","2020年",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021年"]
[null,null,null,null,null,null,null,null,null,null,4,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"K13+1","v":5},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"Z13+1","v":6},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"AO13+1","v":7},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"BD13+1","v":8},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"BS13+1","v":9},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"CH13+1","v":10},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"CW13+1","v":11},null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"DL13+1","v":12},null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"EP13+1","v":2},null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"FE13+1","v":3}]
[null,"日付",null,null,null,null,null,null,null,null,"2020-04-01",{"$f":"K14+2","v":"2020-04-03"},{"$f":"L14+2","v":"2020-04-05"},"2020-04-07","2020-04-09","2020-04-11","2020-04-13","2020-04-15","2020-04-17","2020-04-19","2020-04-21","2020-04-23","2020-04-25","2020-04-27","2020-04-29","2020-05-01",{"$f":"Z14+2","v":"2020-05-03"},{"$f":"AA14+2","v":"2020-05-05"},"2020-05-07","2020-05-09","2020-05-11","2020-05-13","2020-05-15","2020-05-17","2020-05-19","2020-05-21","2020-05-23","2020-05-25","2020-05-27","2020-05-29","2020-06-01",{"$f":"AO14+2","v":"2020-06-03"},{"$f":"AP14+2","v":"2020-06-05"},"2020-06-07","2020-06-09","2020-06-11","2020-06-13","2020-06-15","2020-06-17","2020-06-19","2020-06-21","2020-06-23","2020-06-25","2020-06-27","2020-06-29","2020-07-01",{"$f":"BD14+2","v":"2020-07-03"},{"$f":"BE14+2","v":"2020-07-05"},"2020-07-07","2020-07-09","2020-07-11","2020-07-13","2020-07-15","2020-07-17","2020-07-19","2020-07-21","2020-07-23","2020-07-25","2020-07-27","2020-07-29","2020-08-01",{"$f":"BS14+2","v":"2020-08-03"},{"$f":"BT14+2","v":"2020-08-05"},"2020-08-07","2020-08-09","2020-08-11","2020-08-13","2020-08-15","2020-08-17","2020-08-19","2020-08-21","2020-08-23","2020-08-25","2020-08-27","2020-08-29","2020-09-01",{"$f":"CH14+2","v":"2020-09-03"},{"$f":"CI14+2","v":"2020-09-05"},"2020-09-07","2020-09-09","2020-09-11","2020-09-13","2020-09-15","2020-09-17","2020-09-19","2020-09-21","2020-09-23","2020-09-25","2020-09-27","2020-09-29","2020-10-01",{"$f":"CW14+2","v":"2020-10-03"},{"$f":"CX14+2","v":"2020-10-05"},"2020-10-07","2020-10-09","2020-10-11","2020-10-13","2020-10-15","2020-10-17","2020-10-19","2020-10-21","2020-10-23","2020-10-25","2020-10-27","2020-10-29","2020-11-01",{"$f":"DL14+2","v":"2020-11-03"},{"$f":"DM14+2","v":"2020-11-05"},"2020-11-07","2020-11-09","2020-11-11","2020-11-13","2020-11-15","2020-11-17","2020-11-19","2020-11-21","2020-11-23","2020-11-25","2020-11-27","2020-11-29","2020-12-01",{"$f":"EA14+2","v":"2020-12-03"},{"$f":"EB14+2","v":"2020-12-05"},"2020-12-07","2020-12-09","2020-12-11","2020-12-13","2020-12-15","2020-12-17","2020-12-19","2020-12-21","2020-12-23","2020-12-25","2020-12-27","2020-12-29","2020-01-01",{"$f":"EP14+2","v":"2020-01-03"},{"$f":"EQ14+2","v":"2020-01-05"},"2020-01-07","2020-01-09","2020-01-11","2020-01-13","2020-01-15","2020-01-17","2020-01-19","2020-01-21","2020-01-23","2020-01-25","2020-01-27","2020-01-29","2020-02-01",{"$f":"FE14+2","v":"2020-02-03"},{"$f":"FF14+2","v":"2020-02-05"},"2020-02-07","2020-02-09","2020-02-11","2020-02-13","2020-02-15","2020-02-17","2020-02-19","2020-02-21","2020-02-23","2020-02-25","2020-02-27","2020-03-01",{"$f":"FS14+2","v":"2020-03-03"},{"$f":"FT14+2","v":"2020-03-05"},"2020-03-07","2020-03-09","2020-03-11","2020-03-13","2020-03-15","2020-03-17","2020-03-19","2020-03-21","2020-03-23","2020-03-25","2020-03-27","2020-03-29"]
[null,"マイルストーン",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"▼現況再現完了",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"▼将来配分完了",null,null,null,null,null,null,null,null,null,null,null,null,null,"▼配分特性等整理完了"]
[null,"打合せ　\n【事務所（△）・局（〇）・本省（◎）・委員会または検討会等（●）】",null,null,"計画",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"△",null,null,null,null,null,null,null,null,null,null,"△",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"△",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"△",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"△",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"△"]
[null,null,null,null,"実績",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"△",null,null,null,null,null,null,null,null,null,null,"△",null,null,null,null,null,null,null,null,"△",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"△"]
[null,"（予備）"]
[null,"（予備）"]
[null,"準備計画",null,null,null,"完了","計画","2020-07-05","2020-08-08",{"$f":"IF(I20-H20<0,\"\",I20-H20)","v":34}]
[]
[]
[null,null,null,null,null,null,"実績","2020-07-05","2020-08-08",{"$f":"IF(I23-H23<0,\"\",I23-H23)","v":34}]
[]
[]
[null,"基礎資料収集・整理",null,"資料収集",null,"完了","計画",null,null,{"$f":"IF(I26-H26<0,\"\",I26-H26)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I29-H29<0,\"\",I29-H29)","v":0}]
[]
[]
[null,null,null,"資料整理",null,"実施中","計画","2020-08-01","2020-10-25",{"$f":"IF(I32-H32<0,\"\",I32-H32)","v":85}]
[]
[]
[null,null,null,null,null,null,"実績","2020-08-05","2020-10-25",{"$f":"IF(I35-H35<0,\"\",I35-H35)","v":81}]
[]
[]
[null,"交通量配分用データの作成",null,"OD表",null,"完了","計画","2020-07-20","2020-08-20",{"$f":"IF(I38-H38<0,\"\",I38-H38)","v":31}]
[]
[]
[null,null,null,null,null,null,"実績","2020-07-22","2020-08-22",{"$f":"IF(I41-H41<0,\"\",I41-H41)","v":31}]
[]
[]
[null,null,null,"ゾーニング",null,"完了","計画","2020-07-20","2020-08-20",{"$f":"IF(I44-H44<0,\"\",I44-H44)","v":31}]
[]
[]
[null,null,null,null,null,null,"実績","2020-07-20","2020-08-20",{"$f":"IF(I47-H47<0,\"\",I47-H47)","v":31}]
[]
[]
[null,null,null,"交通量配分道路網の作成",null,"完了","計画","2020-07-20","2020-09-10",{"$f":"IF(I50-H50<0,\"\",I50-H50)","v":52}]
[]
[]
[null,null,null,null,null,null,"実績","2020-07-25","2020-09-20",{"$f":"IF(I53-H53<0,\"\",I53-H53)","v":57}]
[]
[]
[null,"交通量配分用データの作成",null,"現況配分計算",null,"完了","計画","2020-08-20","2020-09-05",{"$f":"IF(I56-H56<0,\"\",I56-H56)","v":16}]
[]
[]
[null,null,null,null,null,null,"実績","2020-08-20","2020-09-10",{"$f":"IF(I59-H59<0,\"\",I59-H59)","v":21}]
[]
[]
[null,null,null,"将来配分計算",null,"実施中","計画","2020-09-06","2020-12-29",{"$f":"IF(I62-H62<0,\"\",I62-H62)","v":114}]
[]
[]
[null,null,null,null,null,null,"実績","2020-09-06","2020-10-10",{"$f":"IF(I65-H65<0,\"\",I65-H65)","v":34}]
[]
[]
[null,null,null,"集計整理",null,"未着手","計画","2020-12-01","2020-12-29",{"$f":"IF(I68-H68<0,\"\",I68-H68)","v":28}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I71-H71<0,\"\",I71-H71)","v":0}]
[]
[]
[null,null,null,"配分結果の整理",null,"未着手","計画","2020-12-01","2020-12-29",{"$f":"IF(I74-H74<0,\"\",I74-H74)","v":28}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I77-H77<0,\"\",I77-H77)","v":0}]
[]
[]
[null,"報告書作成",null,null,null,"未着手","計画","2020-02-01","2020-02-29",{"$f":"IF(I80-H80<0,\"\",I80-H80)","v":28}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I83-H83<0,\"\",I83-H83)","v":0}]
[]
[]
[null,"照査",null,null,null,"実施中","計画",null,null,{"$f":"IF(I86-H86<0,\"\",I86-H86)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I89-H89<0,\"\",I89-H89)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I92-H92<0,\"\",I92-H92)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I95-H95<0,\"\",I95-H95)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I98-H98<0,\"\",I98-H98)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I101-H101<0,\"\",I101-H101)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I104-H104<0,\"\",I104-H104)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I107-H107<0,\"\",I107-H107)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I110-H110<0,\"\",I110-H110)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I113-H113<0,\"\",I113-H113)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I116-H116<0,\"\",I116-H116)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I119-H119<0,\"\",I119-H119)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I122-H122<0,\"\",I122-H122)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I125-H125<0,\"\",I125-H125)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I128-H128<0,\"\",I128-H128)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I131-H131<0,\"\",I131-H131)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I134-H134<0,\"\",I134-H134)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I137-H137<0,\"\",I137-H137)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I140-H140<0,\"\",I140-H140)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I143-H143<0,\"\",I143-H143)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I146-H146<0,\"\",I146-H146)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I149-H149<0,\"\",I149-H149)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I152-H152<0,\"\",I152-H152)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I155-H155<0,\"\",I155-H155)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I158-H158<0,\"\",I158-H158)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I161-H161<0,\"\",I161-H161)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I164-H164<0,\"\",I164-H164)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I167-H167<0,\"\",I167-H167)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I170-H170<0,\"\",I170-H170)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I173-H173<0,\"\",I173-H173)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I176-H176<0,\"\",I176-H176)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I179-H179<0,\"\",I179-H179)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I182-H182<0,\"\",I182-H182)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I185-H185<0,\"\",I185-H185)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I188-H188<0,\"\",I188-H188)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I191-H191<0,\"\",I191-H191)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I194-H194<0,\"\",I194-H194)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I197-H197<0,\"\",I197-H197)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I200-H200<0,\"\",I200-H200)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I203-H203<0,\"\",I203-H203)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I206-H206<0,\"\",I206-H206)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I209-H209<0,\"\",I209-H209)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I212-H212<0,\"\",I212-H212)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I215-H215<0,\"\",I215-H215)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I218-H218<0,\"\",I218-H218)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I221-H221<0,\"\",I221-H221)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I224-H224<0,\"\",I224-H224)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I227-H227<0,\"\",I227-H227)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I230-H230<0,\"\",I230-H230)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I233-H233<0,\"\",I233-H233)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I236-H236<0,\"\",I236-H236)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I239-H239<0,\"\",I239-H239)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I242-H242<0,\"\",I242-H242)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I245-H245<0,\"\",I245-H245)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I248-H248<0,\"\",I248-H248)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I251-H251<0,\"\",I251-H251)","v":0}]
[]
[]
[null,null,null,null,null,null,"計画",null,null,{"$f":"IF(I254-H254<0,\"\",I254-H254)","v":0}]
[]
[]
[null,null,null,null,null,null,"実績",null,null,{"$f":"IF(I257-H257<0,\"\",I257-H257)","v":0}]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"計画"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"実績"]
[]
[null,"【3.作業事項及び対応状況等】"]
[null,"No,","作業事項",null,null,"実施\n状況","作業担当",null,"依頼日","着手日","期限",null,null,null,null,null,null,null,null,"備考"]
[null,null,null,null,null,null,"発注者","受注者"]
[null,{"$f":"IF(C267<>\"\",1,\"\")","v":1},"着手時、経歴書、技術者届等",null,null,"完了",null,"〇","-","-","-"]
[null,{"$f":"IF(C268<>\"\",B267+1,\"\")","v":2},"業務計画書作成",null,null,"完了",null,"〇","-","-","-"]
[null,{"$f":"IF(C269<>\"\",B268+1,\"\")","v":3},"交通量配分用データの作成",null,null,"完了",null,"〇","2020-08-20","2020-08-23","2020-09-10"]
[null,{"$f":"IF(C270<>\"\",B269+1,\"\")","v":""}]
[null,{"$f":"IF(C271<>\"\",B270+1,\"\")","v":""}]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]
[null,""]

{"sheet":"Table","index":1,"n_rows":5,"n_cols":2,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["契約変更","有"]
[null,"無"]
["実施状況","未着手"]
[null,"実施中"]
[null,"完了"]